## Slide 1: 2/6/19 Meeting Update
MacroFab = PROBLEMS

## Slide 2: Agenda
Progress
Next steps
Miscellaneous

## Slide 3: Progress

## Slide 4: Prototype #2 PCB Design - Complete
Processor & Comms boards
  Final design review with Erik - Wed night
  Final changes/updates - Thurs & Fri
  Dropped off parts at Macrofab - Fri (big mix-up here)
  Ordered yesterday
  Potential problem: showing rotated part placement
  Emailed Erik for advice
  Estimated delivery: Feb. 19
Power board
  Attempted to order yesterday
  BGA component (fuel gauge) does not fulfill DRC rules
  Emailed Erik for help
  Looks like we will have to choose a different component

## Slide 5: Comms Code
Progress on this code has stalled due to work on PCB design. Now that the PCBs have been ordered (sort of), I can focus on this a lot more.
Working on sifting through the TI example code to get what we want
Also working on how best to receive the data (e.g. phone UART app?)

## Slide 6: UART Code
Got barebones “closed loop” working (no dust sensor, simply connect Tx and Rx pins on MSP and read Rx Buffer)
Demo with dust sensor not working
Not seeing Tx line on sensor getting pulled low
Possible issues: baud rate (2400) mismatch?

## Slide 7: Action Items

## Slide 8: Action Items
Priority: Fix power board BGA issue - Brady, Rachel
Priority: Rollout second comms board (different antenna) - Robby
Working on comms code - Nathaniel
Working on particulate/UART code - Robyn, Rachel
Working on fuel gauge code - Brady
Scheduling and prepping for meeting next week with sponsors to decide future design directions - Jennifer

## Slide 9: Miscellaneous
Competition not available for submission until March
Gantt Chart